## Sheet1
Project Title |  | LAMP Stack Project
Project Manager |  | Gavin Heaver
Course Name |  | COP4331
Due Date |  | 2026-02-16
Task | Task | Task | Start | Pct pf Task | 1/13 - 1/17 |  |  |  |  | 1/19-1/23 |  |  |  |  | 1/26-1/30 |  |  |  |  | 2/2 - 2/6 |  |  |  |  | 2/9 - 2/13 |  |  |  |  | Presentation
ID | Title | Owner | Date | Complete | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M
1 | Project Management and Design
1.1 | Gantt Chart | Leon W | 2033-03-12 | 0%
1.1.1 | Project Charter Revisions | Kylie R | 2033-03-15 | 0%
1.2 | Research | Pete S | 2033-03-15 | 90%
1.3 | Projections | Steve L | 2033-03-16 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 70%
1.5 | Guidelines | Malik M | 2033-03-18 | 60%
1.6 | Project Initiation | Malik M | 2033-03-23 | 60%
2 | API
2.1 | Scope and Goal Setting | Steve L | 2033-03-24 | 5%
2.2 | Budget | Allen W | 2033-03-29 | 30%
2.3 | Communication Plan | Malik M |  | 0%
2.4 | Risk Management | Malik M |  | 0%
3 | Database
3.1 | Status and Tracking | Pete S |  | 0%
3.2 | KPIs | Leon W |  | 0%
3.2.1 | Monitoring | Kylie R |  | 0%
3.2.2 | Forecasts | Kylie R |  | 0%
3.3 | Project Updates | Pete S |  | 0%
3.3.1 | Chart Updates | Malik M |  | 0%
4 | Frontend
4.1 | Project Objectives | Steve L |  | 0%
4.2 | Quality Deliverables | Allen W |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  | 0%
4.4 | Project Performance | Malik M |  | 0%